## Data
Issue_ID | Issue_Description | Department | Issue_Owner | Issue_Open_Date | Issue_Status | Resolution_Date | Risk_Category | Risk_Rating | Repeat_Issue | Notes
IM-001 | Incomplete customer due diligence documentation | Compliance | Jane Smith | 2023-10-05 | Closed | 2023-11-10 | AML | High | No | Resolved after remediation review | Closed | High
IM-002 | Delayed sanctions screening update | Operations | Michael Brown | 2023-11-02 | Open |  | Sanctions | High | Yes | Awaiting vendor fix | Open | Medium
IM-003 | Missing transaction monitoring alert review | Compliance | Jane Smith | 2023-11-15 | Closed | 2023-12-01 | AML | Medium | No | Process gap identified |  | Low
IM-004 | Outdated ABC training records | HR | Sarah Johnson | 2023-09-20 | Closed | 2023-10-15 | ABC | Low | Yes | Repeat finding from prior audit
IM-005 | Incomplete SAR escalation documentation | Compliance | David Lee | 2023-12-01 | Open |  | AML | High | No | Pending management review
IM-006 | Incorrect risk classification in system | IT | Alex Martinez | 2023-10-18 | Closed | 2023-11-05 | AML | Medium | No | System rule updated
IM-007 | Sanctions list not refreshed on schedule | Operations | Michael Brown | 2023-11-28 | Open |  | Sanctions | High | Yes | Recurring vendor issue
IM-008 | Delayed issue closure documentation | Compliance | Jane Smith | 2023-10-30 | Closed | 2023-12-20 | AML | Low | No | Administrative delay
IM-009 | Incomplete third-party due diligence file | Risk | Emily Davis | 2023-12-05 | Open |  | ABC | Medium | No | Third-party response pending
IM-010 | Transaction monitoring threshold misalignment | IT | Alex Martinez | 2023-09-10 | Closed | 2023-10-25 | AML | High | Yes | Policy updated
IM-011 | Missing audit trail for issue remediation | Compliance | David Lee | 2023-11-12 | Open |  | AML | Medium | No | Documentation in progress
IM-012 | Sanctions escalation delay | Operations | Michael Brown | 2023-12-10 | Open |  | Sanctions | High | Yes | Under investigation
ISS-001 | Incomplete KYC documentation | Retail Banking | J.Smith | 2025-10-02 | Open |  |  | Medium | High | No
ISS-002 | Late SAR filing | Compliance | A.Johnson | 2025-09-18 | Closed | 2025-10-05 | AML | High | Yes | Delay due to system outage
ISS-003 | Vendor due diligence overdue | Procurement | M.Brown | 2025-08-25 | Open |  |  | High | Medium | No
ISS-004 | Transaction monitoring alert backlog | Financial Crimes | L.Wilson | 2025-09-01 | Open |  |  | Medium | High | Yes
ISS-005 | Inaccurate risk scoring model | Risk Analytics | S.Davis | 2025-07-15 | Closed | 2025-09-10 | Model Risk | High | No | Model recalibrated
ISS-006 | Missing audit trail logs | IT Security | R.Martinez | 2025-09-12 | Open |  |  | Medium | Medium | No
ISS-007 | Delayed regulatory response | Compliance | A.Johnson | 2025-08-05 | Closed | 2025-08-28 | Regulatory | High | Yes | Response deadline missed
ISS-008 | Policy exception not documented | Operations | T.Green | 2025-09-20 | Open |  |  | Low | Low | No
ISS-009 | Data reconciliation mismatch | Finance | K.Lee | 2025-09-08 | Closed | 2025-09-15 | Operational | Medium | No | Adjusted entries posted
ISS-010 | Sanctions screening false positives | Financial Crimes | L.Wilson | 2025-08-30 | Open |  |  | High | Medium | Yes
ISS-011 | Incomplete employee training records | HR | M.White | 2025-07-22 | Closed | 2025-08-12 | Compliance | Low | No | Records updated
ISS-012 | Customer onboarding delay | Retail Banking | J.Smith | 2025-09-14 | Open |  |  | Low | Medium | No
ISS-013 | Third-party risk assessment expired | Vendor Management | P.Adams | 2025-06-18 | Open | 2025-07-30 | Third Party | High | No | Renewed assessment
ISS-014 | Unreviewed high-risk customer | Financial Crimes | N.Harris | 2025-09-05 | Open |  |  | Medium | High | Yes
ISS-015 | Incorrect regulatory report submission | Compliance | A.Johnson | 2025-07-10 | Closed | 2025-07-20 | Regulatory | High | No | Corrected and resubmitted
ISS-016 | System access not revoked timely | IT Security | R.Martinez | 2025-08-12 | Closed | 2025-08-18 | Operational | Medium | Yes | Termination delay
ISS-017 | Inconsistent issue documentation | Issues Management | E.Clark | 2025-09-03 | Open |  |  | Medium | Low | No
ISS-018 | Model validation overdue | Risk Analytics | S.Davis | 2025-06-01 | Closed | 2025-09-01 | Model Risk | High | Yes | Resource constraints
ISS-019 | Delayed customer risk review | Wealth Management | D.Patel | 2025-08-20 | Open |  |  | High | Medium | No
ISS-020 | Missing escalation evidence | Issues Management | E.Clark | 2025-09-16 | Open |  |  | Low | Medium | No